## Sheet1
Project | Location | Objective | Description of Key Activities | Key | Time | Estimated | Source of Funds | Lead Agency
Name |  |  |  | Output(s) | Frame* | cost (KSh.M)
Elgeyo Marakwet | Entire county | To enhance sustainable | Acquisition of underground water survey, Rigs, test pumping machine, utility truck for carry casings and vehicle for operations. | Underground water survey | 2023- | 75.00 | CG, World bank, Partners. | CG
County boreholes |  | access to adequate clean |  | machine/Rigs/test pumping | 2027
drilling Rig and |  | water |  | machine/utility truck for carry casings/
equipment |  |  |  | vehicle for operations acquired
Arror Multipurpose | Marakwet West | To enhance sustainable | Construction of multipurpose Arror dam (blue & green water) | Dam with complete water supply | 2023- | 35,000.00 | National Gvt. world bank | National Gvt.
dam |  | access to adequate clean |  | system and irrigation system | 2027
|  | water |  | constructed
Kimwarer | Keiyo South | To enhance sustainable | Construction of multipurpose Kimwarer dam (blue & green water) | Dam with complete water supply | 2023- | 28,000.00 | National Gvt. world bank | National Gvt.
Multipurpose dam |  | access to adequate clean |  | system and irrigation system | 2027
|  | water |  | constructed
Name |  |  |  | Output(s) | Frame* | cost (KSh.M) |  | Agency
Kimanich water | Marakwet | To enhance sustainable | Construction of intake weir, treatment | Complete water supply system (intake, | 2023- | 1,300.00 | CG, world bank, Partners. | CG
project | East | access to adequate clean | works, water analysis lab, supply main, | T-works, supply main, tanks & | 2027
|  | water | masonry tanks, distribution lines, water | distribution lines) constructed
troughs and kiosks.
Sabor dam | Keiyo North | To enhance sustainable | Construction of Sabor dam & | Dams constructed | 2023- | 200.00 | World bank, partners | CG
|  | access to adequate clean | augmentation of existing T-works & |  | 2027
|  | water | pipeline network
Yokot dam | Keiyo North | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 170.00 | world bank,
|  | access to adequate clean |  |  | 2027 |  | CG
water
Moiben –Kuserwo | Marakwet | To enhance sustainable | construction of treatment works, supply | Complete water supply system | 2023- | 110.00 | CG, World bank, partners. | CG
water project | West | access to adequate clean | main, masonry tanks | constructed | 2027
water
Cherelabei water | Kapsowar & | To enhance sustainable | Construction of intake, treatment works, | construction of complete water supply | 2023- | 120.00 | CG, NDMA, world bank, | CG
project | Arror ward | access to adequate clean | supply main, masonry tanks, distribution | system | 2027 |  | Development Partners
|  | water | lines, water troughs and kiosks.
Singore dam | Keiyo North | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 250.00 | CG, NG, Development | CG
|  | access to adequate clean |  |  | 2027 |  | partners
water
Cheboen dam | Keiyo South | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 200.00 | CG, NG, Development | CG
|  | access to adequate clean |  |  | 2027 |  | partners
water
Enou Dam | Marakwet | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 200.00 | CG, NG, Development | CG
| East | access to adequate clean |  |  | 2027 |  | partners
water
Embobut Dam | Marakwet | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 200.00 | CG, NG, Development | CG
| East | access to adequate clean |  |  | 2027 |  | partners
water
Embolot-Kessom Dam | Marakwet | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 200.00 | CG, NG, Development | CG
| East | access to adequate clean |  |  | 2027 |  | partners
water
Embomon Dam | Marakwet | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 200.00 | CG, NG, Development | CG
| East | access to adequate clean |  |  | 2027 |  | partners
water
Jemunada Dam | Marakwet | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 200.00 | CG, NG, Development | CG
| West | access to adequate clean |  |  | 2027 |  | partners
water
Kondabilet dam | Marakwet | To enhance sustainable | Construction of dam | Dams constructed | 2023- | 200.00 | CG, NG, Development | CG
| West | access to adequate clean |  |  | 2027 |  | partners
water
County water pans | County | To enhance sustainable | Construction of water pans | Water pans constructed | 2023- | 200.00 | CG, NG, Development | CG
|  | access to adequate clean |  |  | 2027 |  | partners
water
Name |  |  |  | Output(s) | Frame* | cost (KSh.M) |  | Agency
County Water Training | County | To enhance technical | Establishment and operationalization of | County Water Training Institute | 2023- | 100.00 | CG, WSP
Institute |  | training on water services | County Water Training Institute | established and operationalized | 2027 |  |  | CG
Iten Sewerage system | Iten | To Construct efficient, | Feasibility studies, construction of sewer | Sewage treatment plant constructed, | 2023- | 815.00 | County Government, | NRWWA
|  | effective, and sustainable | lines, treatment plants and effluent | sewer Lines constructed, and effluent | 2027 |  | National Government,
|  | liquid waste management | monitoring laboratories construction and | monitoring laboratories constructed |  |  | NRWWA and
|  | systems | equipping. | and equipped |  |  | Development partners.
Kapsowar Sewerage | Kapsowar | To Construct efficient, | Feasibility studies, construction of sewer | Sewage treatment plant constructed, | 2023- | 610.00 | County Government, | NRWWA
system |  | effective, and sustainable | lines, treatment plants and effluent | sewer Lines constructed, and effluent | 2027 |  | National Government,
|  | liquid waste management | monitoring laboratories construction and | monitoring laboratories constructed |  |  | NRWWA and
|  | systems | equipping. | and equipped |  |  | Development partners.
Kapcherop Sewerage | Kapcherop | To Construct efficient, | Feasibility studies, construction of sewer | Sewage treatment plant constructed, | 2023- | 610.00 | County Government, | NRWWA
system |  | effective, and sustainable | lines, treatment plants and effluent | sewer Lines constructed, and effluent | 2027 |  | National Government,
|  | liquid waste management | monitoring laboratories construction and | monitoring laboratories constructed |  |  | NRWWA and
|  | systems | equipping. | and equipped |  |  | Development partners.
Climate change | Entire | Enhance climate change | Rehabilitation & protection of fragile | Tree growing activities together with | 2023- | 500.00 | CG, World bank, partners | CG
adaptation & | county | mitigation, adaptation, | ecosystems in the entire county, | CC advocacy meetings | 2027
mitigation programs |  | and resilience | Promotion of green energy initiatives, | Solarization of water plumbing systems |  | 500.00
and biogas systems