## Sheet1
195
CHAPTER SIX 6.0 MONITORING, EVALUATION AND LEARNING 6.1 Overview This chapter presents the monitoring and evaluation framework that will guide tracking progress of implementation of proposed CIDP III programmes. Prepared in a participatory process involving all development stakeholders in the County, the CIDP shall also be monitored and evaluated through a participatory approach. Development stakeholders, who include the County and National governments, development partners, the civil society organizations and other interest groups, have been voluntarily integrated into the nine (9) sectors that have been adopted in preparation of this Plan. Coordinated by County Chief Officers of departments under the various sectors, the nine sector groups shall not only be responsible for implementation of proposed CIDP programmes, but also continuous monitoring, evaluation and regular reporting on their status. The sector group monitoring and evaluation reports shall be shared among their members to inform on-going and planned activities and a copy provided to County Monitoring and Evaluation (M&E) Unit for compilation of County Annual Progress Report (C-APR) on implementation of the CIDP. Publication, dissemination and adherence to recommendations of Sector reports and those of the consolidated County Progress reports shall be through the auspices of the Sector Monitoring and Evaluation Committees (SMEC) and County M&E Committee (CoMEC), respectively. Monitoring and evaluation will form a key pillar for knowledge management and organizational improvement and sustainability. This shall promote a culture of learning and application of lessons learnt. This shall entail; sharing of M&E reports and lessons learnt with county departments and other stakeholders for purposes of informing policy, decision making and future program planning, documentation of success stories and good practice for cross learning (county departments and other stakeholders). 6.2 County Monitoring and Evaluation Structure The County M&E functions are domiciled and coordinated at the department of Economic Planning under the Monitoring and Evaluation unit headed by an economist. The county M&E structure is aligned to the County Integrated Monitoring and Evaluation System (CIMES). The unit has designated M&E officers who are M&E focal persons in each department. The officers oversee M&E activities for timely reporting to the department. 196
Monitoring and Evaluation of the CIDP will be done through quarterly Monitoring and Evaluation reports and Annual M&E reports (C-APR). Although not all M&E committees have been operationalized, the department will operationalize the various M&E committees as per the CIMES guidelines namely: The County Intergovernmental Forum (CIF), County Monitoring and Evaluation Committee (CoMEC), Technical Oversight Committee (TOC), Sub-County Monitoring and Evaluation Committee (SCoMEC), Ward Monitoring and Evaluation Committee (WMEC), Sector Monitoring and Evaluation Committee (SMEC) and the village council but in a sequential manner based on existing capacity. The committees will be responsible for developing and validating the CIDP indicator handbooks, review of the M&E policy, tracking and reporting on implementation of various programmes and projects in the CIDP. The committees will also identify and plan for evaluation of various programmes and projects. Figure 6.1 presents the County M&E structure. Figure 6.1: County Monitoring and Evaluation Structure Receive M&E Co-ordination of Provide feedback reports, review development activities for M&E reports and present to and harmonization of and develops county assembly services CIDP County County County Citizen Assembly Intergovernmental Participation Committee Forum Fora Technical Oversight Sector Responsibility and Oversee delivery, County M&E Committees Monitoring and frequency of SMEC at quality, timeliness and Committee Prescribe Evaluation Sector level in support fitness for purpose of (CoMEC) methodologies and Committees of functions of CoMEC M&E reports expert advice (SMEC) in county Sub-‐county, M&E Service Delivery Unit Ward and Village Directorate (SDU) M&E Committees To coordinate County Provides real‐time Integrated M&E information for use by System the CoMEC (CIMES) 197