## Sheet1
Programme 1: Trade development services
Objective: Promote access to and affordable start-ups to traders/groups
Outcome: Improved accessibility to businesses for the MSEs
Sub Programme/Project | Key Outputs | Key Performance Indicators | Targets |  | Remarks
|  |  | Planned | Achieved
Product development services and Mechanization | Number of products developed | Improved incomes for the Jua Kali groups | 1 | 0
Provision of trade revolving fund. | Number of beneficiaries | Improved access to credit facilities | 50 | 0 | No Policy in place
Programme 2 : Market Infrastructural Development services
Objective: To enhance market accessibility to traders
Outcome: Improved working environment for traders
Sub Programme/Project | Key Outputs | Key Performance Indicators | Targets |  | Remarks
|  |  | Planned | Achieved
Rehabilitation of Jimbo market | Rehabilitated market | No. of markets rehabilitated | 1 | 0 | Slow progress in constructio n
Grilling of Samburu modern retail market (KENHA) | Completed stalls with grills | No. of market stalls installed with grills | 1 | 1
Rehabilitation of Jego Open Air Market | Rehabilitated market | No. of markets rehabilitated | 1 | 0 | Delayed procureme nt of the project
Construction of Market Stalls at Kigato Trading centre in Waa Ng'ombeni | Constructed market stalls | No. of market stalls constructed | 1 | 0
Installation of a water tank at Mwangwei | Installed water tank | No. of water tanks installed | 1 | 1