## Sheet1
Programme Name: Roads
Objective: To improve on connectivity for rapid economic development
Outcome: Improved connectivity
Sub Programme | Key Outputs | Key Performance Indicators | Targets |  | Remarks
|  |  | Planned | Achieved
SP1 Roads tarmacking | Kilometers of roads tarmacked | Number of Kilometers of roads tarmacked | 10 | 7.37 | Initial slow mobilization due to Covid- 19
SP2 Roads Opening, grading , | Kilometers of roads Opened | No. of Kilometers Opened | - | 198.99 | A total of 198.99Km were opened