## Sheet1
SP4 Plant machinery and equipment provision | Wheel loader/shovel/Back Hoe procured | Number of wheel loader/shovel procured | 1 | 0 | Inadequate budget allocation.
| Graders procured | Number of graders procured | 0 | 1 | One Motor Grader was procured
| Rollers procured | Number of rollers procured | 1 | 0 | Inadequate budget allocation.
| Bulldozers procured | Number of bulldozers procured | 1 | 0 | Inadequate budget allocation.
| Tracks procured | Number of tracks procured | 0 | 0 | One Truck was disposed
| Excavators procured | Number of excavators procured | 1 | 0 | Inadequate budget allocation.
| Water bowsers procured | Number of water bowsers procured | 1 | 0 | Inadequate budget allocation.
| Low loaders procured/Low Bed | Number of low loaders procured | 1 | 1 | One Low Loader was Procured.
Programme Name: County Public Lighting and Electrification
Objective: To install floodlights for increased business hours and security improvement
Outcome: Improved safety and security of people and property
Sub Programme | Key Outputs | Key Performance Indicators | Targets |  | Remarks
|  |  | Planned | Achieved
SP1 Street Lighting | Improved safety and security of people and property | Number of streetlights schemes | 13 | 4 | The works are ongoing
SP2 Installation of Floodlights in major Centers | Improved safety and security of people and property | Number of floodlights | 14 | 10 | The incomplete High mast are awaiting power connection for them to be operational