## Sheet1
Renovation of Kombani Market sheds | Renovated market shed | No. of market sheds renovated | 1 | 1
Flagship Project Phase III- Fruit Processing Plant in Shimba Hills in Kubo South ward | Constructed fruit processing plant | No. of fruit processing plants constructed | 1 | 0 | Delayed procureme nt of the project
Construction of Lemba (Diani) market | Constructed market | No. of markets constructed | 1 | 0 | Delayed procureme nt
Programme 5 : Investments
Objective: To promote industrial development, manufacturing and value addition
Outcome: Improved income for the farmers.
Sub Programme | Key Outputs | Key Performance Indicators | Targets |  | Remarks
|  |  | Planned | Achieved
Construction of fruit processing plant in Kubo South. | Number of fruit processing plant constructed | Improved income for the farmers. | 1 | 0 | Delayed Funding
Programme 6: Tourism Product Diversification
Objective: Increase Tourism arrivals into the county
Outcome: Attractive and secure destinations.
Sub Programme | Key Outputs | Key Performance Indicators | Targets |  | Remarks
|  |  | Planned | Achieved
Development of Eco- Tourism Site at Maji Moto | Eatery Site and guard rooms constructed | No. of eateries constructed | 1 | 1 | Satisfactor y performanc e
Construction of beach washrooms | Completed washrooms | No. of washrooms constructed | 1 | 1 | Satisfactor y performanc e
Installation of Bio-Digester | Installed Bio- Digester | No. of digesters installed | 2 | 0 | Delayed NEMA approval
Construction of Signages | Constructed signages | No. of signages | 2 | 0 | Delayed KeNHA approval
Programme: ICT Infrastructure Development
Objective: Enhance County Connectivity
Outcome: Enhance Resource sharing
Sub Programme | Key Outputs | Key Performance Indicators | Targets |  | Remarks
|  |  | Planned | Achieve d