## Sheet1
|  | primary to secondary |  |  | Number of girls | 17,100 | 34,200 |  | 0 | No budget allocation
supplied with
sanitary towels
Program Name: Sports, Arts and Talent development
Objective: To improve arts, sports and talent development
Outcome: Enhanced competitiveness in Arts, Sports and talents
Sub programme | Sub | Key Output |  | Key Performance Indicators |  | Baseline |  | End | Achievement | Remarks | Remarks
| programme | [6 empty] | Term
Target
SP1 Sports, arts and talent infrastructural development |  | Improved infrastructure for sports, arts and talent development |  |  | Number of | 0 | 1 | 1 | 1 | Phase three
stadiums
established
[5 empty] | Number of | 13 | 60 |  | 47 |  | Insufficient
[5 empty] | sports fields | [5 empty] | budgetary
[5 empty] | rehabilitated | [5 empty] | allocation.
|  |  |  | Number of academies established | Number of | 0 | 10 |  | 5 |  | 5-satellite
[5 empty] | academies | [5 empty] | academies
[5 empty] | established | [5 empty] | established.
Insufficient
budgetary
allocation.
[5 empty] | Number of | 0 | 1 |  | 1 | achieved | achieved
Performance
arts talent
centers
constructed and
equipped
SP2 Sports, arts and talent competition |  | Improved competitivenes s |  |  | Number of | 100 | 100 |  | 110 | achieved
sports
competitions
held
[5 empty] | Number of | 720 | 720 |  | 720 | achieved
teams
participated
[5 empty] | Number of | 10 | 10 |  | 10 | achieved
disciplines
involved
SP3 Support services |  |  | Enhanced |  | Amount of | 30M | 30M |  | 36m | achieved
|  |  | support to |  | support in
|  |  | teams |  | Kenya shillings
Program Name: Community empowerment
Objective: To achieve inclusivity and empower community for equitable and sustainable development
Outcome: Enhanced inclusivity and participation of community in development
Sub programme | Sub | Key Output |  | Key Performance Indicators |  | Baseline |  | End | Achievement | Remarks | Remarks
| programme | [6 empty] | Term
Target
SP1 Youth, women and PWDs fund |  | Enhanced empowerment |  | Amount disbursed |  | 52M | 48M | 48M | 0 |  | Late
enactment
of the
legislation.