## Sheet1
Risk Category | Risk | Risk Implication | Risk Level (Low, Medium, High) | Mitigation measures
Sector: Finance, Economic Planning and County Development
Leadership and Governance | Inadequate collaboration between the executive and the county assembly | Impediment of the achievement of the County Government’s agenda and mandate | Medium | - Ensure a collaboration framework is in place to build good relations between different arms of government. - Organize leadership and governance training for the various cadres of leaders within the County - Organize joint planning meetings for coordinated development in all areas. - Promote high ethics and integrity standards among all staff
Financial | Inadequate financial resources | -Poor returns from investments. -Failure to manage assets / liabilities or to obtain value for money from the resources deployed, and / or non-compliant financial reporting. | Medium | - Ensure compliance with all provisions of the PFM Act 2012 and all other related regulations about finances - Where possible conduct value for money assessments on projects being undertaken by the County. - Consider other sources of funds from other quarters by the County - Undertake budget training for stakeholders to ensure an understanding of budget making and management
Technological | High Dependency on technology to run county operations | Below optimal delivery of public services | High | - Develop a digitization strategy for the county services. - Develop an implementation matrix for the technological uptake for county services. - Conduct an ICT surveillance survey for security and vulnerability of County systems - Develop a Cyber security strategy
Climate Change | Drought | Loss of livestock and reduced crop productivity | High | - Climate smart agricultur practices
Organizational (people/staffing) | Inadequate human resource capacity | Inefficiency in service delivery | Medium | - Timely recruitment
Infrastructural development | Inadequate capacity to carry out infrastructural development | Failure to achieve economic and social goals | High | - Develop, review, and update the County’s infrastructural development plans with all stakeholders. - Build capacity for skills and equipment to carry out infrastructural development within the County
Operational (Service Delivery) | Low quality of services delivered | Inefficient service delivery | High | - Develop, review, and update the service delivery for all the County services. - Develop a mechanism for tracking the adherence to the service charter - Deploy an enforcement mechanism for the service charter requirements.