## Sheet1
No |  | Policy/ Plan/ | Evaluation Title (specify the type) | Outcome(s) | Use of the Evaluation Findings | Commissioning Agency/ Partners |  | Expected |  | Expected |  | Evaluation | Source of Funding
|  | Programme/ | [5 empty] | Evaluation |  | Evaluation |  | Budget (Ksh.
|  | Project | [5 empty] | Start date |  | End date |  | Million)
1. | CID P 2023- 2027 |  | 3rd CIDP Mid-term Review (MTR) | Improved efficiency of the CIDP implementation | Inform decision making for implementation of prioritized programmes for the plan period | Department of Finance and Economic Planning | Jul. 2026 |  | Sept. 2026 |  | 12 |  | CGN/ Development Partners
2. | CID P 2023- 2027 |  | 3rd CIDP End-term Review (ETR) | Improved decision- making necessary for formulation and implementation of future plans | Provide baseline data for future plans; Inform decision-making in selection and implementation of future policies and programmes | Department of Finance and Economic planning | Jul. 2028 |  | Sept. 2028 |  | 15 |  | CGN/ Development Partners
3. | Cou nty Spatial Plan 2019-2029 |  | MTR of the County Spatial Plan 2019- 2029 | Enhanced productivity & sustainability in use of land and compliance with land use plans | Inform decision making for implementation of prioritized spatial development strategies for the plan period | Department of LPPHUD | Jul. 2025 |  | Sept. 2025 |  | 60 |  | CGN
4. | You th, Sports, Gender and Social Services Strategic plan 2023-2027 |  | MTR/ETR of strategic plan 2023- 2027 | Improved efficiency in the delivery of the prioritised Key Result Areas (KRAs) | Inform decision making for implementation of prioritized KRAs and their impact on service delivery | Department of Youth, Sports, Gender and Social Services | Jul. 2026/Jul. 2028 |  | Sept. 2026/Sept. 2028 |  | 5 |  | CGN
5. | Tra de, Cooperatives, Tourism and Industrialization Strategic plan 2021-2026 |  | ETR of departmental strategic programmes | Improved efficiency in the delivery of the prioritised KRAs | Inform decision-making in selection and implementation of future programmes and strategies | Department of Trade, Cooperatives, Tourism and Culture | Jul. 2026 |  | Sept. 2026 |  | 10 |  | CGN
6. | Ima risha Barabara Programme |  | MTR of Imarisha Barabara Programme | Improved rural and urban road connectivity | Inform future designing and implementation of the programme | Department of Infrastructure / NTSA | Jul. 2026 |  | Sept. 2026 |  | 8 |  | CGN/ Development Partners
7. | Agr iculture sector programmes (crop, livestock and fisheries) |  | Impact evaluation of agriculture sector programmes on food security | A food secure County | Inform and refine prioritised policies, programmes and projects aimed at improving food security in Nakuru County | Department of Agriculture, Livestock and Fisheries/ KNBS | Jul. 2026 |  | Jun. 2027 |  | 10 |  | CGN/ Development Partners
8. | ECD E infrastructure |  | Rapid evaluation on adequacy and quality of County | Improved access to quality early childhood development education | Inform future infrastructural development needs | Department of Education, ICT, e- | Jul. 2027 |  | Sept. 2027 |  | 3 |  | CGN/ Development Partners
|  | Programme/ | [5 empty] | Evaluation |  | Evaluation |  | Budget (Ksh.
|  | Project | [5 empty] | Start date |  | End date |  | Million)
| development programme |  | ECDE infrastructure |  |  | Government and Public Communication
9. | Wa ter and sewerage management programme |  | Impact evaluation on efficacy of County water and sewerage projects | Increased access to potable water and sewerage services within the County | Inform strategic interventions to improve water and sewerage coverage within the County | Department of Water, Environment, Energy, Natural resources and Climate Change | Jul. 2025 |  | Dec. 2025 |  | 5 |  | CGN
10. | Env ironmental Management Programme |  | Impact evaluation on effectiveness of solid waste management and pollution control interventions by the County government | Clean, secure and sustainable environment | Inform strategic interventions to improve environmental management practices | Department of Water, Environment, Energy, Natural resources and Climate Change | Jul. 2027 |  | Sept. 2027 |  | 3 |  | CGN/ Development Partners
11. | Prim ary Care Networks (PCNs) |  | Rapid evaluation of established and functional PCNs | Increased access to quality preventive and promotive health services | Inform the strategic interventions to address emerging gaps in the delivery of quality primary health services | Department of Health Services | Jul. 2025 |  | Sept. 2025 |  | 5 |  | CGN/ Development Partners
12. | Hea lth infrastructure development (County Level IV facilities) |  | Rapid evaluation on functional optimality of existing County Level IV health facilities | Increased access to quality health services | Inform the strategic interventions to address capacity gaps in County level IV health facilities to match recommended standards of care | Department of Health Services | Jul. 2025 |  | Sept. 2025 |  | 5 |  | CGN/ Development Partners
13. | Voc ational Training Centres Capitation Grant |  | Impact evaluation on capitation grant to VTCs and vocational training graduates | Improved access to quality vocational training | Inform strategic interventions to improve uptake of vocational training programmes | Department of Education, ICT, e- Government and Public Communication | Jul. 2027 |  | Sept. 2027 |  | 2 |  | CGN
14. | Nat ional Agricultural and Rural Inclusive Growth Project (NARIG-P) |  | Outcome evaluation of NARIG-P in Nakuru County | Improved agricultural productivity and profitability | Inform strategic interventions in the succeeding National Agricultural Value Chain Development Project (NAVCDP) | Department of Agriculture, Livestock and Fisheries | Apr. 2024 |  | Jun. 2024 |  | 4 |  | CGN/GoK/ Development Partners
15. | Dig ital training programmes |  | Outcome evaluation on effectiveness of training forums at the digital centres | Improve digital literacy and access to online jobs | Inform strategic interventions to improve digital literacy and uptake of digital opportunities | Department of Education, ICT, e- Government and Public Communication | Jul. 2027 |  | Sept. 2027 |  | 1 |  | CGN/ Development Partners