## Sheet1
Programme Name: ECDE Service Improvement
Objective: To Improve access to equitable quality education
Outcome: Improved access to equitable quality education
Sub Programme | Key Output | Key Performan ce Indicators | Linkage s to SDG Targets | Planned Targets and Indicative Budget (KSh. M) | [9 empty] | Total Budget (KSh
|  |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5
|  |  |  | Target | Cost | Target | Cost | Target | Cost | Target | Cost | Targe t | Cost
ECDE Feeding | Increased enrolment and attendance | Number of learners enrolled | Quality Educatio n (SDG 4) | 12300 | 17 | 12600 | 17.5 | 12900 | 18 | 13200 | 18.5 | 13500 | 19 | 90
ECDE Capitation | Increased enrolment | Amount of fund allocated | Good health and well being (SDG 3) | 12300 | 12.3 | 12600 | 12.6 | 12900 | 12.9 | 13200 | 13.2 | 13500 | 13.5 | 64.5
Digital Learning | Quality education | No. of learners enrolled | Quality Educatio n (SDG 4) | 3000 pupils | 3.6 | 3000 pupils | 1.8 | 3000 | 1.8 | 3000 | 1.8 | 3000 | 1.8 | 10.8
ECDE Infrastructure and Equipment Improvement | Improved infrastructure | No. classrooms constructed and equipped | Quality Educatio n SDG 4) | 20 | 20 | 20 | 20 | 20 | 20 | 4 Model ECDE (1 per Subcount y) | 60 | 4 | 60 | 180
TOTAL BUDGET |  |  |  |  | 52.9 |  | 51.9 |  | 52.7 |  | 93.5 |  | 94.3 | 345.3