## Sheet1
Risk Category | Risk | Risk Implication |  | Risk Level (Low, | Mitigation measures
Medium, High)
Unavailability of land | Lack of space for development | No or slow development | High |  | Acquisition of land
Poor Mobility | Poor supervision of projects | Poorly executed projects | Medium |  | Timely Maintenance of motor vehicles
Social | Disintegrated families and rotten society | Loss life, broken families, poor health, low productivity | High |  | Public campaigns, enforcement and establishment of rehab centers
Awareness | Illiteracy | Unproductive society | high |  | Sensitization and creation of awareness
Gender responsive budgeting | Inadequate financial resource | Delay in implementation of gender programs | high |  | Look for financial support from various developments
Child protection | Lack of awareness | Increase in number of Street families | high |  | Sensitization and creation of awareness on children’s rights and protection
Policies | Lack of policies | Delay in implementation of programs and projects |  |  | Gaps assessment, analysis and formulation of policies
Organizational | -Inadequate Human Resource Capacity -Lack of policy development -Poor mobility | -Inefficiency in service delivery -Absurd development -Inability to actualize intended project purpose -Eroding investor confidences -Poor supervision of projects | Medium |  | -Have sound policies in place -Timely human resource development and review -Timely Maintenance of motor vehicles
Political | -Lack of political goodwill -Political interference | -Conflict of interest -Selective projects implementation | High |  | -Proper and well-structured public participation and civic education
Land | -Slows down economic growth | -No service delivery -Conflict of interest across the divide | High |  | -Develop and fully implement proper land policy