## Sheet1
[12 empty] | Planned Targets and Indicative Budget (KSh. M) | [19 empty] | Budg
|  |  |  | Key |  |  |  | Baseline
Sub | [5 empty] | SDG | [5 empty] | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | et
|  | Key outputs |  | performance
Programme | [5 empty] | linka | [25 empty] | (Kshs
|  |  |  | indicators |  |  |  | Year |  | Value |  | Target |  | Cost |  | Target |  | Cost |  | Target |  | Cost |  | Target |  | Cost |  | Target |  | Cost
[6 empty] | ges | [25 empty] | . M)
|  | undertaken |  | land resources
initiatives
undertaken
| Community sensitization fora on land market operations held |  | Number of Community sensitization fora on land market operations held |  | 2.3 |  | 2022 |  | - |  | 1 |  | 2 |  | - |  | 0 |  | 1 |  | 2 |  | - |  | 0 |  | 1 |  | 2 |  | 6
|  | Capacity building |  | Number of |  | 2.3 |  | 2022 |  | - |  | 1 |  | 0.3 |  | - |  | 0 |  | 1 |  | 0.3 |  | - |  | 0 |  | 1 |  | 0.3 |  | 0.9
|  | initiatives of |  | Capacity
|  | enforcement officers |  | building
|  | on land laws and |  | initiatives of
|  | physical plans held |  | enforcement
officers on
land laws and
physical plans
held
| Community sensitization fora on land lease agreement protection measures held |  | Number of community sensitization fora on land lease agreement protection measures held |  | 2.3 |  | 2022 |  | - |  | 1 |  | 1 |  | - |  | 0 |  | 1 |  | 1 |  | - |  | 0 |  | 1 |  | 1 |  | 3
|  | Community |  | Number of |  | 1b |  | 2022 |  | - |  | 3 |  | 0.5 |  | - |  | 0 |  | 3 |  | 0.5 |  | - |  | 0 |  | 3 |  | 0.5 |  | 1.5
|  | sensitization fora on |  | community
|  | existing land policies |  | sensitization
|  | and laws held |  | fora on
existing land
policies and
laws held
| Community sensitization fora held to promote land consolidation for efficient production |  | Number of community sensitization fora held to promote land consolidation for efficient production |  | 1b |  | 2022 |  | - |  | 9 |  | 0.6 |  | 9 |  | 0.6 |  | 9 |  | 0.6 |  | 9 |  | 0.6 |  | 9 |  | 0.6 |  | 1.8
|  | Government land with |  | Proportion of |  | 2.3 |  | 2022 |  | 10 |  | 30 |  | 2 |  | 40 |  | 2 |  | 50 |  | 2 |  | 60 |  | 2 |  | 70 |  | 2 |  | 10
|  | title deeds |  | government
land with title
deeds