## Sheet1
| Step No. |  | Description |  | Details |  | Time Frame |  | Responsibilities
1. |  | Preliminaries |  | Concept Note Circular CIDP Technical Team SWGs Sensitization |  | 30th June, 2022 |  | County Executive Committee Member (CECM) Economic Planning County Secretary (CS)
2. |  | Data Collection and Analysis |  | Review Priority setting and public participation forums Sector policies Governor Manifesto |  | 31st July 2022 |  | (SWG, CIDP TEAM) Economic and Planning Director
3. |  | Development of Objectives and Strategies |  | Vision Mission Objectives Strategies |  | 31st July, 2022 |  | CECM Economic Planning County Chief Officer(CCOs) Economic and Planning Director
4. |  | Formulation of Programmes and Projects |  | Programmes Sub programmes Projects Resource Mobilization Risk Management Development of specific sector priorities |  | 31st August 2022 |  | CECM Economic Planning CCOs Economic and Planning Director
5. |  | Preparation of the Draft CIDP |  | Shared Peer Review |  | 30th September 2022 |  | CIDP Technical Team
6. |  | Validation |  | Stakeholders workshop |  | 30th November 2022 |  | CECM Economic Planning Economic and Planning Director Principal Secretary, State Department for