## Sheet1
Name | Location | Objective |  | Description of Key Activities |  | Key Output(s) |  | Time Frame |  | Estimated | Source of Funds | Lead Agency
cost (KES.
Billion)
Mother-Child Health Centre | Embu County Headquarters | Reduced morbidity and mortality of mother and child within Embu community |  | Maternity unit; Gynecology unit, Neo-natal unit; Neo- natal intensive care unit; Paediatric unit; Paediatric ward; Paediatric Intensive care unit; MCH/FP clinic; Maternity theatre |  | Mother-Child Health unit constructed and operationalized |  | 2023- 2026 | 0.5 |  | National Government; County Government; Donors | Health Dept
4 Mother's Baby Units In 4 Sub-Counties. | Manyatta, Runyenjes, Mbeere North, Mbeere South sub counties |  | Reduced | Maternity unit; Gynecology unit, Neo-natal unit; Paediatric ward; MCH/FP clinic; Maternity theatre |  | 4 Mother baby centers constructed and operationalized |  | 2023- 2026 | 0.4 |  | National Government; County Government; Donors | Health Dept
morbidity
and
mortality of
mother and
child within
Embu
community
Mental Health Complex | Embu County Headquarters |  |  | Wards; Rehabilitation centers; Psycho-social center; ECT Theatre; |  | Mental Health Complex constructed and operationalized |  | 2023- 2025 | 0.5 |  | National Government; County Government; Donors | Health Dept
Cancer Diagnostic and Treatment Center | Embu County Headquarters |  |  |  | Comprehensive |  | Cancer center | 2023- 2026 | 0.5 |  | National Government; County | Health Dept
[5 empty] | cancer center |  | unit constructed
[5 empty] | construction and |  | and
[5 empty] | operationalization: |  | operationalized