## Sheet1
Project Name | Location | Objective |  |  | Description of Key Activities | Key Output(s) |  |  | Time Frame |  | Estimated |  | Source of Funds | Lead Agency
Cost
(KES.M)
subsidy program
Livestock production
Construction of Honey processing plant | Kiambere |  | To enhance |  | Construction and equipping of the Honey processing plant. |  | Completion of |  | 2023 - 2027 | 500 |  |  | County funds Developme nt partners | Livestock production department
|  |  | value |  |  |  | construction
|  |  | addition of |  |  |  | works.
|  |  | honey and |  |  |  | Installation honey
|  |  | honey by |  |  |  | processing
|  |  | products |  |  |  | equipment
Establishment of feeds factory |  | To decrease cost of production |  |  | Construction of feed factory; Recruitment of quality assurance staff; Installation of machine and equipment; | Improved feeds quality and quantity; |  |  | 3 years | 550 |  |  | National and County Government and developmen t partners | Livestock department
Cost
(KES.M)
Establishment of Embu Creameries | Ugweri | To reduce post-harvest losses and increase income |  |  | Construction of milk processing plant; Installation of machine and equipment; KEBS certification | Tons of milk aggregated; Tons of milk processed | 2 years | 700 | 700 |  |  | National |  | Livestock and Cooperative department
Government
; County
Government
;
Developme
nt partners
VET
Launch Livestock products-based cottage industries | Sub-county |  | Empower |  | Create a livestock- based cottage industry hub. | Sustainable cottage enterprises for creation of job and income opportunities | 2023- 2027 | 200 |  |  | National Government ; County Government ; Developme nt partners |  |  | Department of Veterinary Services
youth and
women to
generate
income and
develop
industries
from
processing
livestock
products and
by-products
Construction of Leather Processing Plant | Ishiara | Leather value addition |  |  | Land acquisition (10 acres); Construction and equipping of the | Building and installation of leather processing unit Processed leather products | 2023- 2025 | 500 |  |  | County funds Developme nt partners |  |  | Department of Veterinary Services
Cost
(KES.M)
leather processing plant;
Fisheries
Aquaculture Business Development Programme (ABDP) |  | Embu County | Aquaculture development | Identification of project areas; Participatory Rural Appraisal; Selection of beneficiaries Supply of inputs; | Quantity of fish produced | Eight years (2018 – 2026) | 2000 |  |  | IFAD; GOK; Beneficiary | Aquaculture Business Development Programme (ABDP), County fisheries sub sector
Co-operative Development
Formation of Embu County multi- purpose cooperative Union |  | All wards | To service all sectors cooperatives in the county | Operationalize the county multi- purpose cooperative union | Embu County multi- purpose cooperative Union in place | 5 years | 600 |  |  | National government; County government; Developme nt partners; Other stakeholders ; | Trade and industry Cooperatives Agriculture Development partners