## Sheet1
Sub-Programme |  |  | Performance |  | Targets |  |  | Achievements | Comments
Indicator
Embu Solar Park |  |  | No. of solar |  | 1 |  |  | 0 |  | Project was to be done
|  |  | power | [6 empty] | through PPP but was not
|  |  | established | [6 empty] | implemented.
Mini Hydro Plants |  | No. of mini hydro stations established |  |  | 3 |  |  | 0 | Project not done
Programme: Public Housing
Public housing infrastructure development |  | No. of affordable housing units constructed |  |  | 5000 Units |  |  | 0 | The project was to be done through PPPs but it was not achieved
|  | No of official residence constructed |  |  |  | 2 Official |  | 1 Residence for Governor | The Governors Official residence is at 60% complete
Residence
for
Governor
and Deputy
Governor
Housing Development project for the elderly persons |  | No. of housing units constructed for the elderly persons |  |  | 2000 |  |  | 0 | Project not done
Development of affordable and alternative building Materials |  |  | Types of |  | Done in all Sub- Counties |  |  | Done in all Sub- Counties | The project was done in all sub-counties
affordable
building
materials
(prefab)
developed,
bricks
Rehabilitation of existing Government houses |  | No. of houses renovated |  |  | 100 |  |  | 0 | Project not done
Housing land |  | No. of acres of land purchased |  |  | 37 |  |  | 0 |  | Project not done
Indicator
Programme: General Administration Planning and Support Services
Human Resource development and staff compensation |  |  | No of employees remunerated |  |  | 22 | 22 |  |  | All the staff were remunerated
|  |  |  | No. of Staff |  | 19 | 19 |  |  | All staff were trained
trained
Office Support and administrative Service |  |  | No. of staff supported |  |  | 22 | 22 |  |  | Staff were supported to undertake their duties
Policy and legal framework development |  |  |  | No. of legal |  | 5 | 3 |  |  | Three laws were enacted.
frameworks and
policies
developed
Programme: Trade Development
Boda boda and Market Sheds |  |  |  | No. of boda boda |  | 100 |  | 100 |  |  | Target was achieved.
sheds constructed
|  |  | No, of markets sheds constructed |  |  | 20 | 29 |  |  | Target was achieved.
Capacity Development |  |  |  | No. of trainings |  | 50 | 247 |  |  | Formation of functional associations helped to achieve the target.
conducted on
management of
markets
Joint Loans Board and Micro Credit Programme |  |  | No. of SMEs loaned |  |  | 500 | 0 |  |  | The target was not achieved.
Weights and measures |  |  |  | No. of traders |  | 5000 | 2497 |  |  |  | There was a major challenge in
|  |  |  | sensitized on | [6 empty] | the inadequate staffing, no
|  |  |  | weights and | [6 empty] | provision of tools and lack of
|  |  |  | measures | [6 empty] | vehicles for routine inspections.
Alcohol and licensing |  |  | No. of Alcohol licenses issued/facilities inspected/No. of inspections conducted |  |  | 10000 | 8900 |  |  | In 2020, alcohol establishments were closed due to Covid-19 pandemic.
| Product |  |  | No. of products |  | 50 | 10 |  |  |  | Business performance was low
| development |  |  | identified | [6 empty] | due to the COVID 19 pandemic.