## Sheet1
Sub Programme |  |  |  | Key |  | Targets | Achievements | Remarks
|  |  |  | performance | [5 empty] | a ,
Indicators
| Construction and |  |  | No. of water |  | 4 | 1 | This achieved target was undertaken in collaboration with CDF |  | a ,
| expansion of |  |  | treatment plant | [5 empty] | a ,
| water treatment |  |  | constructed and | [5 empty] | a ,
| plant |  |  | expanded
Water distribution services |  |  | No. of households connected |  |  | 80,000 | 39,000 | The target was not fully achieved. However,39,000 households were connected with safe drinking water |  | a ,
| Boreholes for |  |  | No of boreholes |  | 40 | 30 |  | Seventy Five percent of the | a ,
| ground water |  |  | Drilled and |  |  |  |  | target was achieved with thirty | a ,
| abstraction |  |  | equipped |  |  |  |  | boreholes drilled and equipped | a ,
Spring /Well development |  |  | No. of springs developed |  |  | 20 | 3 | This was not fully achieved due to the issue of land ownership which affected its implementation. Some of the springs are in privately owned land. |  | a ,
Five Hills water Project |  |  |  | No of Hills |  | 5 | 4 | This was achieved in Mwea, Makima Mavuria and Kiambere |  | a ,
reservoirs
|  |  |  | 0perationalised | [5 empty] | a ,
Construction of 4 mega dams |  |  | No. of dams constructed |  |  | 4 | 0 | This was not achieved |  | a ,
Programme: Sanitation services
Sanitation Services |  |  | No. of sewer systems constructed, renovated, and relocated |  |  | 6 | 1 | One sewer system was constructed through EWASCO |  | a ,
Programme: Expansion of irrigated area and Provision of Irrigation water | [9 empty] | a ,
Development of irrigation schemes |  |  | No of irrigation schemes developed. |  |  | 25 | 8 | Eight Irrigation schemes were developed and operationalized. |  | a ,
| Intake works and |  |  | No. of intakes |  | 40 | 9 | Nine Intakes were constructed |  | a ,
| pipelines |  |  | constructed | [5 empty] | a ,
Construction of night storage reservoirs |  |  | No of reservoirs Constructed |  |  | 8 | 0 | The target was not achieved |  | a ,
performance
Indicators
Promotion of Drip systems |  | No of drip |  | 50 | 2 | Two irrigation drip system were developed
systems
developed
Programme: Environment and Natural Resource Conservation and Management
Participatory and sustainable Environment management and conservation |  | No. of hills |  | 15 | 2 |  | Two public hills were
|  | reforested |  |  |  |  | reforested
| No. of woodlot established |  |  | 4 | 2 | Two woodlots were established
| No. of kms of river bank pegged and protected |  |  | 1000 Kms | 20Kms |  | This was not fully achieved.
However, communities were
sensitized on the importance of
protecting land area along river
banks
Solid Waste Management | No of dumping site in place |  |  | 75 | 46 | 46 dumpsites were commissioned in markets
|  | No. of |  | 6 | 3 | Three projects were promoted through development partners
environmentally
friendly
technologies
promoted
Participatory Forest Resource Management | % of land under forest and tree cove- in gazette areas and farm lands |  |  | 15 | 12.9 | This was achieved through development partners
Climate Change Adaptation and Resilience |  | Number of |  | 180,000 | 150,000 | This was achieved through development partners
people
participating in
climate smart
activities
Development of Mining Industry | No. mineral and other natural resources mapped |  |  | 14 | 2 | Copper and Iron Ore resources mapped.
| No. of minerals exploited |  |  | 5 | 3 |  | Sand Harvesting, Stone
Quarrying, Gravel minerals
were exploited.
Meteorology | No of weather briefs |  |  | 72 | 72 | This was achieved through development partners
performance
Indicators
|  | No of advisories |  | 10 | 10 |  | This was achieved through
|  | prepared and |  |  |  |  | partners like NDMA and
|  | disseminated |  |  |  |  | Metrological