## Sheet1
riSK CAtEGory | riSK | riSK imPLiCAtion | riSK LEvEL (LoW, mEDium, hiGh) | mitiGAtion mEASurES
Financial | Inadequate financial resources | Stalled and/or slow imple- mentation of projects Poor service delivery | Medium | • Enhanced resource mobilisation through collection of own source reve- nue and support from development partners
l a w f | Late Disbursement of Funds | Stalled and/or slow imple- mentation of projects Poor service delivery |  | • Prepare a procurement plan early to allow for departments to organise for financial requisitions from the exchequer. • Negotiate contracts with adequate grace period to cover for the delays in fund disbursement.
l a w f | Inefficient utilisation of resources | Stalled and/or slow imple- mentation of projects Poor service delivery |  | • Implement the recommendations of the Capacity Assessment and Ratio- nalisation of the Public Service. • Ensure full enforcement of existing government assets management frameworks.
l a w f | Pending bills | Increase in project cost beyond the budget estimates |  | • Ensure timely implementation of projects so that the county is not disad- vantaged by time value of money. • Ensure proper project design and costing
Process Risk | Ineffective planning and Implementation Process | Bad governance, poor service delivery |  | • Ensure robust public participation for community ownership of govern- ment initiatives (projects and programs) • Sufficient legal and administrative framework to support government Initiatives
l a w f | Ineffective Procure- ment | Stalled and/or slow imple- mentation of projects Poor service delivery |  | • Strict adherence to Public Procurement and Disposal Act, 2015 • Adequate Technical support from departments for efficient procurement processes .