## Sheet1
NO | Policy/ Programme/ Project | Evaluation Title | Outcome(s) | Use of the Evaluation Findings | Commissioning Agency/ Partners | Anticipated Evaluation startdate | Anticipated Evaluation end date | Evaluation Budget(Kshs.) | Source ofFunding
1 | CIDP | Midterm Review of the CIDP III and development of CIDP 4 | Improved implementation of the CIDP | Improve implementation ofCIDP. | CEC Finance and Economic Planning | June 2025 | Sept2025 | Kshs. 35million | GoK/ Donor
2 | Policy, Planning, General administration and support Services | End term evaluation of policies and support services | Effective delivery of policy, and support services | To Increase Institutional Efficiency and Effectiveness in Extension Service Delivery | CEC Agriculture & Livestock | June 2027 | Sep 2027 | Kshs. 6.6 million | HBC/ Donor
3 | Crop, Land & Agribusiness Development services | End term evaluation | Enhanced Food Security and Improved Livelihoods for county residents | To increase agricultural productivity and outputs | CEC Agriculture & Livestock | June 2027 | Sep 2027 | Kshs. 50.1 million | HBC/ Donor
4 | Food security Enhancement | End term evaluation of food security Enhancement | Enhanced Food Security and Improved Livelihoods for county residents | To ensure food security in the county | CEC Agriculture & Livestock | June 2027 | Sep 2027 | Kshs. 85.5 million | HBC/ Donor
5 | Livestock Development Services | End term evaluation of livestock Development Services | Increased Livestock production and productivity | To promote, regulate and facilitate livestock production for socio-economic development and industrialization | CEC Agriculture & Livestock | June 2027 | Sep 2027 | Kshs. 148.68 million | HBC/ Donor
6 | Blue Economy and Fisheries Development Services | End term evaluation | Enhanced food security and improved livelihoods | To increase fisheries productivity and output | CEC Blue Economy, Fisheries, Mining, and Digital Economy | June 2027 | Sep 2027 | Kshs. 91.3 million | HBC/ Donor
7 | Blue Economy Development Services | End term evaluation of Blue Economy Development Services | Accelerated development and employment opportunities | Optimize exploitation and utilization of the wetlands and the catchment areas for wealth creation | CEC Blue Economy, Fisheries, Mining, and Digital Economy | June 2027 | Sep 2027 | Kshs. 322.75 million | HBC/ Donor
8 | Lands and Physical Planning | End term evaluation of Lands and Physical Planning | Guided physical developments | To provide a spatial framework that would guide, develop, administer and manage Land and its activities within the county | CEC Lands, Physical Planning, Housing, and Urban Development | June 2027 | Sep 2027 | Kshs. 56.9 million | HBC/ Donor