## Sheet1
Organisation | Technical | Poor service delivery | • Recruitment of competent staff • Strengthen departments that carries out design review, procurement support, construction supervision and test run support to control design and construction quality to ensure efficient and effective delivery
| Absorption | Poor service delivery | • Undertake monthly and quarterly implementation reporting of all county projects and programmes to ensure effective and efficient delivery • Strict adherence to financial procedures and procurement regulations • Staff put on performance contracting and ensure targets set relate to county development plans and policies.
| Inadequate legal Framework | Poor service delivery | • Develop requisite legal and policy framework
| Change Manage- ment | Poor information dissemina- tion and action | • Exhaustive disseminate the CIDP III to ensure that each of the stake- holders understand their role in contributing towards its implementa- tion and achieving the county vision.
Exogenous Risks | Natural calamities (disasters) | Interruption and/or Stalling of government services | • Establish Emergency Fund as per The Public Finance Management Act, 2012 section 110 to mitigate emergencies
| Political risks | Changes in holders of politi- cal offices or shift in political economy may completely derail the programmes and projects. This will delay delivery of the vision of the CIDP in the programmed period. | • Entrench institutionalism in the County Government
| Court cases | Litigations and court injunc- tions can also derail timely execution of the CIDP. | • Strict adherence to laws and regulation in County operations