## Sheet1
Issue | Proposals to address listed issues in CIDP III
Covid-19 pandemic caused delays in project execution | • Disaster preparedness as guided by the relevant department.
Landslides and floods in some areas that caused massive destruction of water infrastructure | • Set aside contingency funds to assist during emergencies.
Solarization of pumping scheme as part of climate change mitigation measure | • Shift from the use of fossil fuels to green energy in pumping schemes.
Emergence of informal settlements within urban areas | • Development of informal settlement upgrading and prevention strategy • Development of urban infrastructure within informal settlements.
Lack of axle load testing sites | Establish testing sites along the main roads (KeNHA)
Limited funding | Resource mobilization
High cost of construction | Source alternative appropriate building materials
Disaster occurrences | Establish a disaster response team fully equipped and trained
Encroachment of road reserves | develop roads policy and enact a law for implementation
Inadequate resources (technical staff, equipment & building materials) | Employ & train qualified staff, acquire new appropriate equipment and plant, adopt new emerging technologies for building.
Insecurity along the valley | creating buffer zones and opening of more access roads
natural calamities | Incorporating climate response to road infrastructure
Road failure (overloading, vandalism etc.) | Engage all development partners to enforce.
non-motorized traffic | incorporate in the design all partisan parties and enforce traffic control measures
project reconnaissance | Corry out reconnaissance prior to implementation carry out Annual Roads Inventory and Condition Surveys (ARICS)
roads data | develop road register develop spatial maps.
maintenance | All developed infrastructure must be put under maintenance immediately
climate resilient designs | incorporate the requisite measures on all developments
Need for synergy among stakeholders | Engage all stakeholders.
Overall Implementation of Competency based curriculum | Improve on management / administration of CBC
Phasing out of 3-year-olds in Pre-primary education | Establishment of daycare centres to cater for the 3-year- olds.
Community engagement, sensitization and awareness is key for effective implementation of education programs | Develop citizen engagement framework
Capacity gap in curriculum delivery | Training and capacity building to facilitate effective curriculum delivery. Provision of capitation grants promote access to quality education.
Timely data collection is essential for objective decision making | Timely collect and update gender disaggregated data for objective decision making
Adequate and safe educational infrastructure promotes nondiscrimination in access to quality education | Develop disability friendly infrastructure and learning materials
School feeding program attract and retain learners in school system | Implement school feeding program.
Digital learning is efficient and effective in education system | Implement digital learning in both ECDE and VTC centres
Cultural erosion (e.g. Commercialization of Traditional/ herbal medicine, emergence of LGBTQ etc) | Preservation of cultural practices and knowledge
Increasing Teenage Pregnancies | Enhance In of school mentorship programs and Out of schools Social life skills training
COVID 19 pandemic | Enhance mitigation and empowerment programmes
Sport medicine, Sports Nutrition and injury management | Adoption of modern sports practices
Community involvement promotes ownership and goodwill in implementation of programmes | Develop public engagement frameworks
Monitoring and Evaluation is a key component in ensuring value for money is realized. | Undertake frequent inspections on projects and strengthen county M&E unit
Partnership approach is key for effective and efficient implementation of programmes and projects in the Sector; | Source for more development partners
Involvement of men and boys in gender issues is essential for realization of gender equality | Develop guidelines which provide for men and boys participation in gender issues and women empowerment.