## Sheet1
Project | Location | Objective | Description of Key Activities | Key | Time Frame* | Estimated cost (KSh. | Source of Funds | Lead Agency
Name |  |  |  | Output(s) |  | Million)
Affordable Housing Programme | Chebiemit | of affordable housing within the County. | documentation of land for affordable housing programme • Construction of affordable housing units. | affordable housing units. |  |  | Government • National Government • Development partners | National Government.
Informal settlements Improvement | Chebiemit, Cheptongei, Kapcherop, Kapsowar, Bugar, Tambach | Improve living conditions and strengthen security of tenure in informal settlements in selected towns. | • Infrastructural developments & Security of land tenure | • No. of Informal settlement upgraded | 2023-2027 | 140.00 | • County Government • KISP II | County Government & National Government
Wind Power Generation Plant | Elgeyo Marakwet Escarpment | Promote Green energy production | • Establishment of wind power generation plant | • Wind power generation plant established | 2023-2027 | 2,700.00 | • County Government • National Government • Development partners | County Government
Solar Power Generation Plant | Elgeyo Marakwet Escarpment | Promote Green energy production | • Establishment of solar power generation plant | • Solar power generation plant established | 2023-2027 | 6,500.00 | • County Government • National Government • Development partners | County Government
Sustainable Urban Economic Development (SUED) Programme
Urban: Town square & Stimulus Market | Iten Municipality | Promote market infrastructural facilities | • Development of policy framework for public private partnership • Construction of modern stimulus market and town square | • Public private partnership policy developed. • Constructed Modern stimulus market and town square | 2023-2027 | 1,130.00 | • Public and Private funding | County Government
Drainage improvement | Iten Municipality | Improved storm water drainage. | • Preparation of a drainage system plan, Improvement, and maintenance of existing | • Drainage system plan prepared, Km | 2023-2024 | 79.00 | • Public Funds • IFI • NGOs | County Government
Name |  |  |  | Output(s) |  | Million)
|  |  | drainage features. | of storm water drainage improved and maintained |  |  | • IFI • County Government • NGOs • National Government
Upgrading of Municipal roads | Iten Municipality | Improved road network and urban corridors | • Upgrading of urban roads within iten municipality | • Km. of road improved | 2024-2027 | 1,305.80 | • Public Funds • NGOs • IFI • County Government • NGOs • National Government | County Government
Waste Management | Iten Municipality | Establishment of a proper waste disposal mechanisms, Adequate waste management facility, Improved waste collection | • Excavation and haulage of dumped material to new landfill. Site • remediation and restoration work. • Commissioning of a new waste management facility • Establishment of an integrated waste collections system | • Existing dumpsite remediated and restored. • No. of waste management facility established. • Integrated waste collection system established. | 2023-2027 | 750.00 | • Public Funds • IFI • NGOs • County Government • NGOs • National Government | County Government
Improved wastewater and sanitation services | Iten Municipality | Establishment of proper liquid waste management mechanisms and improved sanitation, Improved sanitation | • Acquisition of wastewater exhauster trucks • Establishment of a decentralized wastewater treatment system, Installation of public toilets on the running tracks | • No. of exhauster trucks acquired. • Establishment of a wastewater decentralization facility, No. of public toilets installed | 2023-2027 | 827.20 | • County Government • PPP • IFI • NGO • National Government | County Government & National Government
Name |  |  |  | Output(s) |  | Million)
Enhancement of streetlighting, green energy generation and use | Iten Municipality | Improved streetlighting, green energy use and generation | • Review of current implementation plan and current commercial and technical arrangements. • Design study to ensure suitable coverage of target area (roads, markets, and trails)" • Installation of solar refrigeration system • Establishment of a landfill biogas generation plant • Establishment of renewable energy generation at Kessup Falls • Establishment of renewable energy generation at Singore | • No. of streetlights units installed. • No of solar refrigeration systems installed. • Landfill entailing biogas generation established. • Kw Generated from renewable energy, • No. of HH connected with electricity | 2023-2026 | 424.00 | • Public Sector Funds • IFI • Donor • private funds • PPP • County Government • NGO • National Government | County Government
Water Supply System | Iten Municipality | Improved rainwater harvesting & Increased water supply | • Enhanced rainwater harvesting • Construction of Sabor dam | • No. of rainwater harvesting points established. • Sabor Dam constructed, functional and adequately equipped. | 2024-2027 | 1,903.00 | • County Government • PPP • IFI • NGO • National Government | County Government
Potato VC processing plant | Iten Municipality | Reduction in post- harvest losses and provision of ready off take of potatoes | • Construction of a potato processing plant | • Potato processing plant established. • No. of farmers benefited from the factory. • Tonnage of potatoes processed. | 2023-2025 | 2,500.00 | • SUED programme with potential for other public and private funding involvement | County Government