## Sheet1
Risk Category | Risk |  | Risk Implication |  |  | Risk Level | Mitigation measures
(Low, Medium,
High)
Strategy Risks | Pursuing a strategy that is poorly defined and based on inaccurate data. |  | Failure to achieve programme/project outcomes. |  | Medium | Medium |  | Proper project
identification, formulation
and implementation,
Enable risk-based
decision making and
strategy setting.
Governance Risks | Failure to embed risk management in governance |  | Ineffective decision-making affecting performance. |  | Medium |  |  | Improve accountability in
management of county
resources,
Improve the ability to
identify, evaluate and
manage threats.
Legal Risks |  | Claims made by the | Lack of public trust since the image of the county government is affected. |  | High |  | The County Government of Kilifi will put in place appropriate measures to meet all legal and regulatory requirements. | The County Government
|  | public that may result | [5 empty] | of Kilifi will put in place
|  | to liability or loss to | [5 empty] | appropriate measures to
|  | the County | [5 empty] | meet all legal and
|  | Government; | [5 empty] | regulatory requirements.
Financial Risks |  | Financial |  | No value for money from | High |  |  | Strict adherence to Public
|  | mismanagement. |  | the resources allocated on |  |  |  | Financial Management
|  |  |  | programmes. |  |  |  | principles.
Technology Risks |  | Sudden change in |  | Old technology becomes | Low |  | Continuous capacity building of staff on new technology. | Continuous capacity
|  | technology. |  | obsolete; |  |  |  | building of staff on new
|  |  |  | Staff unable to use new |  |  |  | technology.
technology
Information Risks | Unavailability of accurate data. | Unavailability of | Poor project implementation, planning and budgeting. | Poor project | High |  |  | Improve data collection
|  | accurate data. |  | implementation, planning |  |  |  | methods so as to inform
|  |  |  | and budgeting. |  |  |  | planning and budgeting in
the county.
Security Risks | Cybercrime; Cyber-attack; Cyberterrorism. |  |  | Access to information by | High |  | Network security; Application security; Information security; Operational security and end user education. | Network security;
|  |  |  | the citizenry is affected; |  |  |  | Application security;
|  |  |  | Loss of relevant |  |  |  | Information security;
|  |  |  | information and data; |  |  |  | Operational security and
|  |  |  | Loss of funds; |  |  |  | end user education.