## Sheet1
| Kilometers of roads graveled | No. of Kilometers Graveled | 40 | 60.9 | A total of 60.90Km were Graveled
| Kilometers of Cabro Paved roads | No. of Kilometers Cabro Paved | - | 1.7 | A total of 1.7Km were Cabro Paved
SP3 Bridges, drifts and Culverts | Bridges/Box culverts constructed | Number of bridges constructed | 2 | 1 | 1 Box culverts done at Mkilo, 1 Bridge (Mteza Bridge) is still in Design Stage
| Drifts constructed | Number of Drifts constructed | 30 | 11 | 11 Drifts were constructed
| Lines of Culverts Installed | No. of Lines Installed | - | 316 | 316 Lines were installed
SP4 Storm water Drainage system | Storm water Drainage systems constructed | Number of system constructed | 1 | 0 | Inadequate budget allocation.
SP5 Demarcation of County Roads | Kilometers of Roads Demarcated | No. of Kilometers Demarcated | - | 10 | 10Km of County roads were demarcated
Programme Name: Public Works And Government Buildings
Objective: To improve access and sustainability of physical Infrastructure and public works affiliated
Outcome: Improved connectivity
Sub Programme | Key Outputs | Key Performance Indicators | Targets |  | Remarks*
|  |  | Planned | Achieved
SP1 Government buildings | County & staff buildings rehabilitated | Number of buildings /staff houses rehabilitated | 10 | 5 | Adequate budget allocation is key to facilitate Renovation works.
SP2 Fire stations constructed | Fire stations constructed | Number of fire stations constructed | 0 | 0 | Inadequate budget allocation.
| Fire engines procured | Number of fire engines procured | 1 | 0 | Inadequate budget allocation.