## Sheet1
County Assembly Registry | County Assembly Complex | Safe of Custody of Assembly documents and access point |  Fixing and fitting the registry with cabinets  Digitizing the registry | Registry fully equipped | 2024- 2027 | 10 | CGK | County Assembly
Walk- through security and Luggage scanners | County Assembly Complex | Provide security to the premise, Members and staff |  Provision of Walk through scanner  Installation of luggage scanner | Installation of the scanners | 2023- 2024 | 14 | CGK | County Assembly
Public utilities to Ward Offices | Ward Offices | Provide clean and safe utilities |  Provision clean utilities  Installation of gutters for water catchment | Utilities build and in use | 2023- 2024 | 100 | CGK | County Assembly
Drilling of boreholes | Ward Offices | Provision of clean water |  Drilling of boreholes in the ward offices | Boreholes drilled | 2023- 2024 | 80 | CGK | County Assembly
Parking sheds with green energy installation | County Assembly Complex | Provide safe parking areas for the Members Provide back-up green energy to the Assembly complex |  Building and installation of parking sheds  Installation of solar panels on the roof of parking sheds  Installation of domestic grade wind turbines for energy generation.  Installation of battery storage for solar & wind energy | Parking sheds build | 2024- 2027 | 88 | CGK | County Assembly
Water Fountain | County Assembly Complex | Beautificatio n of the Assembly Complex |  Installation of water fountain at the Complex building open to sky area | Water fountain installed and working | 2024- 2027 | 4 | CGK | County Assembly
Perimeter wall | Ward Offices | Enhance security at the ward offices. |  Building of perimeter walls at the ward offices | Perimeter walls build | 2024- 2027 | 100 | CGK | County Assembly
Grilling of non- | County Assembly | Enhance security at the Complex |  Installation of grills at the ground floor | Grills installed | 2024- 2027 | 10 | CGK | County Assembly