## Sheet1
Project Name | Location | Objective | Description of Key Activities | Key Output(s) | Time Frame |  | Estimated |  | Source of Funds | Lead Agency
a f f o r | [6 empty] | Cost (Ksh. |  |  | t e
a f f o r | [6 empty] | Million) |  |  | t e
Construction of a modern multi-purpose agro-processing centre | Nakuru County ATC, London ward | To establish a large-scale dairy and horticultural processing plant for enhanced value addition and increased shelf life of dairy and other horticultural products | Feasibility study; Land acquisition (5 acres); Design and planning; Construction; Purchase and installation of machinery; Project operationalisation | Dairy and horticultural processing Centre complete and operational | 2023- 2027 | 922 |  |  | CGN; Nakuru County Dairy Union; National Government; Development Partners | Department of Agriculture, Livestock and Fisheries
Development of affordable housing | Nakuru City, Naivasha Municipality, Gilgil Municipality and Molo Municipality | To provide affordable housing units to County residents | Pre-feasibility & feasibility studies; Undertake PPP approvals; Procurement of responsive bidders; Project implementation and commissioning | 6,000 housing units constructed | 2023 – 2027 | 10,000 |  |  | CGN; Development Partners; National Government | LPPHUD Private partners
County titling programme | Countywide (Public Land) | Regularization of plots in urban areas and public land inventory | Data collection; planning & surveying; Inventory; documentation and titling | Urban centres with approved plans; Urban plots surveyed; Title deeds for County utility land and urban plots | 2023- 2027 | 500 |  |  | CGN; Development Partners; | LPPHUD
Refurbishment of Afraha stadium phase II | Biashara- Nakuru East | To complete the construction of Afraha Stadium to an International standard | Public participation; Project design and planning; ESIA; Project procurement; Project implementation and commissioning | Afraha Stadium completed to International Standards | 2023 – 2027 | 800 |  |  | World Bank; Development partners; CGN; State Department for Housing and Urban Development; Ministry of Culture and Sports | Nakuru City Board; Department of YSGSS; Athletics Kenya; Ministry of Culture and Sports
Cost (Ksh.
T a b | [6 empty] | Million)
Nakuru International Conference Centre | HQ | To meet the diverse needs and enhance revenue collection | Feasibility and prefeasibility studies; Conduct EIAs; Design and planning; Project implementation; | Nakuru International Conference Centre | 2023- 2027 | 1,200 |  |  | CGN; Development partners | Nakuru city Board
Naivasha multipurpose stadium | Naivasha Municipality | To enhance talent development and improve recreational and cultural activities | Feasibility and prefeasibility studies; Conduct EIAs; Design and planning; Project implementation; | Naivasha multipurpose stadium constructed | 2023 – 2027 | 2,500 |  |  | CGN; Development partners | Naivasha Municipal Board; Department of YSGSS
Upgrading of Maraigushu Karai-St. Theresa-Mirera Inn Road to Bitumen standards | Naivasha Municipality | To improve connectivity and enhance economic growth | Prefeasibility and feasibility studies; Conduct EIAs; Design and planning; Project implementation | 11 Km of road/NMT upgraded to bitumen standard and drainage | 2023 – 2027 | 600 |  |  | CGN; World bank; | Naivasha Municipal Board; Department of Infrastructure
[7 empty] | Cost (Ksh. |  |  | e s
Million)
School feeding programme | All public ECDEs | To improve child nutrition, enrolment and retention | Piloting; Procurement of milk suppliers; Distribution; | All public ECDE’s learners under school feeding programme | 2023-2027 | 1,200 |  |  | CGN; Development partners | Directorate of Education
Construction and equipping of Vocational Training Centres of Excellence | All Sub- Counties | To establish model VTCs for improved access to quality of vocational training | Prefeasibility and feasibility studies; Conduct ESIA; Acquisition of land (where necessary); Design and planning; Project implementation | 11 Centres of Excellence Constructed and equipped | 2023-2027 | 500 |  |  | CGN; Development partners | Directorate of Vocational training
Nakuru bulk water supply project (Itare Dam) | Kuresoi North | To increase supply of water to Kuresoi North & South, Molo, Rongai, Njoro, Nakuru East, & Nakuru West sub-counties | Construction of dam; Treatment Works; Tunnel; Storage tanks; laying of gravity mains and distribution lines | 222,223 households benefiting from 105,000m3 of potable water per day | 2023-2027 | 35,000 |  | GoK; Development Partners | CRVWWDA ; CGN; WSP
Malewa Dam Water Supply Project | Naivasha | To increase supply of water to Naivasha & Gilgil sub-counties | Construction of dam; Treatment works; Storage tanks; Laying of gravity mains and distribution lines | 152,667 households benefiting from 45,000m3 of potable water per day | 2023-2027 | 20,000 |  | GoK; Development Partners | CRVWWDA ; CGN; WSP
Turasha Water Supply Project | Gilgil | To increase supply of water to Gilgil Sub-County | Rehabilitation of Turasha Dam; Raw Water Pipeline; Treatment Works; Laying of distribution network | 50,000 households benefiting from 15,000m3 of potable water per day | 2023-2027 | 550 |  | GoK; Develop ment Partners; | CRVWWDA ; CGN; WSP
Njoro Bulk Water Supply project (Egerton Dam) | Njoro | To increase supply of water to Njoro Sub-County | Construction of dam; Treatment Works; Storage tanks; Laying of gravity mains and distribution lines | 164,000 households benefiting from 35,000m3 of potable water per day | 2023-2027 | 6,000 |  | GoK; Development Partners | CRVWWDA ; CGN; WSP
Naivasha Town Water Supply Project | Naivasha | To increase supply of water to Naivasha Municipality | Feasibility studies; Designs and planning; Drilling five boreholes; Expanding distribution network; Purchase and supply of Zonal/consumer meters; Construction of ten 50m3 water storage tanks; Construction of water kiosks | 50,000 households benefiting from 4,500m3 of potable water per day | 2023-2027 | 500 |  | Development Partners; GoK | CRVWWDA ; CGN; WSP