## Sheet1
Project Name | Location | Objective | Description of Key Activities | Key Output(s) | Timeframe | Estimated Cost (Kshs.) | Source of Funds | Lead Agency
sports equipment & materials
Social Protection, Culture and Recreation
2 mega warehouses for food and non- food storage | Garsen, madogo | To provide storage for food and no-food | Land/ cite identification Public participation Feasibility study Development of designs and BOQs Tendering process Actual construction | Improved storage capacity at sub counties Improved timely responses to emergencies | 1 yr | 500M | CGTR and partners | CGTR
Construction of Water pan / irrigation construction | Hakoka, Assa Kone, Bangale | To reduce scarcity of water in the county and improve food security | Land/ cite identification Public participation Feasibility study Development of designs and BOQs Tendering process Actual construction | Improved water accessibility for both livestock and human Enhanced food security Reduced migration of livestock Reduced conflict among pastoral communities | 2 yr | 500M | CGTR and Partners | CGTR
Environment Protection, Water and Natural Resources Sector
Construction of a dam wall at Matomba broo | Garsen Central ward | To enhance access to water for irrigation | Site Clearance, Excavation and Earthworks Inlet Structure and Filtration Gallery Water Draw-off System Concrete and Masonry Works Fencing Works |  |  | 3B |  | CWWDA
Construction of 90km Bura- Chifiri-Wayu water pipeline | Wayu ward | To enhance access to clean and safe water |  |  |  | 2.5B |  | CWWDA
Bura-Hola water pipeline project and upgrading of the Bura water works | Chewele & Chewani wards |  | Construction of 50Km 12" HDPE PN16 |  |  | 2.0B |  | CWWDA
Madogo- bangale water pipeline project |  |  | Construction of 50Km 16" - 10 “ HDPE PN16 - |  |  | 5.0B |  | CWWDA