## Sheet1
| Step |  | Risk Management
| Step 1 |  | Is the risk strategic, tactical or operational? What is the potential
| Understand |  | outcome (or outcomes)?
| the risk |  |  Strategic – compromises organization’s principles, e.g., corruption
| context |  |  Operational – leads to key services not being delivered or delivered
adequately, e.g., power failure
 Tactical – results in cost overruns and/ or project delays
Step 2 Identify the risk |  | Is it natural, accidental or intentional? What does it impact on (safety, environment, and performance)? Natural e.g., risk of physical damage and long-term environmental impact due to weather events such as storms, earthquakes or volcanoes Accidental e.g., service disruption due to power failure or increased demand due to refugee influx Intentional e.g., social unrest, protests
| Step 3 |  | What is the likelihood an event will occur, and what are the
| Evaluate |  | consequences if it does? What and who will be affected?
Consider public health and safety (e.g., hospitals, traffic lights) as well as
financial implications for businesses. Also consider running different scenarios
to understand how the impact of an event will scale, potentially causing
cascading failure across multiple systems.
You can score from 1 (low) to 3 (high) or expand the scale to factor in more
considerations (I.e., 1 to 5).
The resulting grid is used to determine the risk.
|  |  |  | d o o h i l e k i l | Consequence
[6 empty] | Low | Moderate | High
[6 empty] | <20% | 20-50% | > 50%
[6 empty] | affected | affected | affected
High
>50% chance
Moderate
20-50% chance
Low
<20% chance
Remember that critical assets often have the highest risk levels.
For example, what is the risk of a power failure? First, we assess the likelihood.
If we have not been properly maintaining the system, it will be moderate to
high. The consequence will depend on how widespread the failure is, how long
it lasts, who is affected and how many we anticipate will be affected. For a
hospital or local businesses, this will be high; for homes, moderate to low.
Step 4 Manage |  | How will you deal with the risk? (Three options) a. Avoid the risk b. Mitigate the risk by reducing or altering the consequences of a threat or hazard or, by reducing the likelihood of it occurring in the first place. c. Accept the risk. For example, we can mitigate the consequence of a power failure by having backup generators. We can also mitigate the likelihood through proper maintenance and inspection of the power equipment.
| Step 5 |  | Did it work as well as hoped? What would you do differently?
Measure