## Sheet1
2.4 Challenges | Experienced | during Imple | mentation of t | he previous CID | P
i. Legal, instit | utional and p | olicy framewo | rk:
Departments an | d directorates | attributed low | achievements t | o inadequate po | licy, legal
and institution | al framework. | In some sect | ors efforts to | develop policy | and legal
framework wer | e delayed in t | heir approval a | nd enactment | processes thus | hindering
delivery of servi | ces.
ii. Resource M | anagement:
Inadequacies in | three key reso | urces hindered | the realization | of targets:
a. Human Re | source: Huma | n resource was | indicated as ina | dequate across | all sectors
in terms | of numbers a | nd skills. This | was largely d | ue to existing | freeze on
employme | nt and limite | d career pro | gression. The | departments th | us faced
challenges | in succession | management a | nd staff stagnati | on.
b. Tools and | Equipment: La | ck of necessary | equipment an | d facilities was re | ported in
various d | epartments. In | addition, the | re was inadeq | uate office spa | ce which
hampered | efficient opera | tions and perfo | rmance.
c. Financial | Resources: Ina | dequate and | untimely disbu | rsement of fun | ds led to
delayed e | xecution of pro | grammes. De | lay in payment | of pending bill | s, budget
reviews ne | gatively affecte | d projects impl | ementation.
iii. Acquisit | ion of land fo | r projects:
Various sectors | experienced | challenges in a | cquiring land | for government | projects.
There was cons | istent land use | conflicts and u | navailability as | well as exaggera | ted value
of land. This led | to delays in de | livering on som | e projects.
iv. Climate | change:
The effects of a | dverse impact | of climatic cha | nge which resu | lted in increase | d weather
variability were | experienced | in this period | . This affected | food producti | on, water
supply, livestoc | k production, | infrastructural | development a | nd general livel | ihoods of
the people. Th | ere was need, | therefore, for | enhanced inve | stments toward | s climate
change mitigati | on and adaptat | ion.