## Sheet1
Project | Location | Objective | Description of Key Activities | Key | Time Frame* | Estimated cost (KSh. | Source of Funds | Lead Agency
Name |  |  |  | Output(s) |  | Million)
County GIS Lab | Iten | Adequate infrastructure for lands, physical planning and mapping of county resources | • Establishment and operationalisation of a County GIS Lab | • A well- equipped and operational GIS Lab | 2023-2025 | 30 | • County Government • national Government • Development partners | County Government
County Spatial Plan | Countywide | Enhance well- coordinated land uses and Development | • Initiation, base mapping, scoping and data collection, situational analysis and synthesis of key planning issues, visioning, plan formulation and associated outputs, Plan compilation and packaging, plan approval and gazettement. | • Approved County Spatial Plan | 2024-2026 | 89.00 | • County Government • national Government • Development partners | County Government
Elgeyo Marakwet Ardhi House | Iten | County based Ardhi House established, improved land processes. | • Establishment of a County based ardhi house | • Well established and operational ardhi house | 2023-2027 | 60.00 | • National Government and development partners | County Government and National government.
Disaster Management | County | Establishment and operationalization of Firefighting Services and mitigation measures against incidences of disasters. | • Purchase of firefighting engines • Equipping and operationalization of the Fire station. | • 2 fire engines & assorted firefighting equipment, • 1 fully equipped and operational fire services unit. | 2023-2027 | 150.00 | • County Government • National Government • Development partners | County Government
Elgeyo Marakwet | Iten, Tambach, | Support implementation | • Identification and | • No. of | 2023-2027 | 2,000.00 | • County | County Government and