## Sheet1
List | Proposal to address listed issues
Complementing hardware with skills capacity building of beneficiaries enhances project success rate | Public sensitization on balancing resource allocation to both hardware and software
Positive engagement with political leaders builds goodwill and synergy that helps to unlock some of the local barriers affecting project implementation | Create and/or strengthen structures for consultation between the two arms of government
A stakeholder approach to actions and processes develops unity, cohesiveness and synergy among value chain actors and promoters | Strengthen structures for consultation and collaboration among sector stakeholders
Timely resource allocation and disbursement significantly influences programme/ project delivery | Enhance institutional efficiency and effectiveness in resource disbursement and implementation of projects
Supporting beneficiaries with free materials without any contribution from beneficiaries results in low levels of ownership | Change the approach from “free” to “cost sharing” where beneficiaries meet a proportion of the cost