## Sheet1
Name | Location | Objective |  | Description of Key Activities | Key Output(s) | Time Frame |  | Estimated | Source of Funds |  | Lead Agency
cost (KES.
Billion)
Government; Donors
Upgrading Ishiara to Level 5 | Mbeere North Sub County | To improve the health services to the Embu community |  | Renal unit OPD/ Casualty Mother baby unit | Ishiara level 5 Upgraded and operationalized | 2023- 2026 | 0.5 |  | National Government; County Government; Donors |  | Health Dept
Upgrading Runyenyes Level 4 To Level 5 | Runyenjes Sub County |  | To improve | Renal unit OPD/ Casualty Mother baby unit | Runyenjes level 5 Upgraded and operationalized | 2023- 2026 | 0.5 |  |  | National | Health Dept
|  |  | the health | [6 empty] | Government;
|  |  | services to | [6 empty] | County
|  |  | the Embu | [6 empty] | Government;
|  |  | community | [6 empty] | Donors
Upgrading Karurumo to An Ideal Training Center | Runyenjes Sub County | To improve the training standards of the health care workers in Embu County |  | Construction of hostels, 2 wards (female/paed), theatre, morgue radiology dept, ablution block (water coset), training hall, biodigester (40M), upgrade lab to class D, incinerator and resource Centre with Internet. -ambulance -Equip/instruments -Internet | Ideal training center operationalized | 2023- 2027 | 0.5 |  | National Government; County Government; Donors |  | Health Dept
M | [7 empty] | cost (KES.
Billion)
-asbestos removal - macerator machine
Modern Level 4 In Gategi | Mbeere South Sub County |  | To improve | Theater, X ray, mortuary, OPD/Casualty | Gategi Modern level 4 constructed and operationalized | 2023- 2026 | 0.5 |  | National Government; County Government; Donors | Health Dept
the health
services the
Mwea sub
county
community