## Sheet1
Sub-Programme |  |  | Key |  | Targets | Achievements | Comments
Performance
Indicators
Programme: General Administration Planning and Support Services
Health workforce development and improvement |  | No. of health workers remunerated |  |  | 1300 | 1041 | The reduction of staff was due to retirements, designations and natural attrition.
Performance
Indicators
|  |  | No. of health workers recruited. | No. of health |  | 1900 | 51
workers
recruited.
|  |  | No. of health workers promoted |  |  | 2900 | 159 | The expectation was for promotion of all health workers but only 159 was achieved
|  |  |  | No. of health |  | 500 | 0 | There were no health workers that were absorbed
workers
absorbed
|  |  | No. of health workers outsourced |  |  | 25 | 1 | The officer outsourced was an oncologist. For effective Outsourcing model will be sorted upon approval of the health bill
|  |  | No. of staff trained |  |  | 800 | 41
Health policy, planning and financing |  |  | No. of County strategic plans prepared |  |  | 1 | 0 | There is a draft strategic plan which is at the finalization stage but is yet to be approved
|  |  |  | No. of County |  | 5 | 5
Annual Work
Plans prepared
|  |  | No. of Annual reviews of County health Strategic and Investment Plans undertaken |  |  | 5 | 5 | The department has been conducting periodical progress review meetings of County health Strategic and Investment Plans
| Health |  |  | No. of quarterly |  | 20 | 20 | Quarterly data review meetings were held
| information |  |  | data review
| system |  |  | meetings held.