## Sheet1
Sub-Programme |  | Key | Targets | Achievements | Comments
|  | Performance |  |  |  |  | o f
|  | Indicators |  |  |  |  | o f
| No. of public facilities with integrated established Electronic Medical records |  | 80 | 32 | The process was phased based on capacity and financial allocations |  | o f
|  | No. of County | 5 | 0 | Sector M&E TWG was not established due to the many competing priorities. |  | o f
|  | Health Sector |  |  |  |  | o f
M&ETWG
established
| No. of facilities connected through ICT |  | 25 | 2 | Embu Level 5 hospital and Runyenjes There was no ICT focal person in the department only at level 5 hospital. Further, the target was not clear on mandate |  | o f
| No. of health services computerized |  | 370 | 259 |  | All outpatients’ services are
[6 empty] | computerized. 40% of | o f
[6 empty] | inpatient and theatre services | o f
[6 empty] | in level 5 and level 4 | o f
[6 empty] | hospitals. | o f
| No. of Tele medicines operationalized |  | 5 | 2.5 | The operationalization is in progress at the level 5 hospital. However, a few additional computers/monitors are needed and the inter-linking (connections)
|  | No. of Queuing | 5 | 0 | No Queuing system was established
system
established
Health Infrastructural development | No. of health facilities completed |  | 52 | 10 | There were many facilities that were under construction. Prioritization was undertaken which led to non-achievement of the target.
Performance
Indicators
|  | No. of cancer | 1 | 0 | The Cancer Management centre was not constructed. |  | a l
management
centres
constructed
| No. of OPD/Casualty complexes constructed |  | 1 | 0 | The OPD/Casualty complex was not constructed. |  | a l
Research | No. of operational research done |  | 15 | 6 |  | Conducted eight operational
researches on COVID,
[6 empty] | cancer, pneumonia, | a l
Diarrheal, in children and
nutrition
| No. of health surveys conducted |  | 4 | 4 | The department has conducted four surveys, KDHS and two nutrition surveys. (Universal child benefit pilot program in Nthawa,Reproductive Health Maternal, Neonatal ,Child,Adolescennt Health(RMNCAH), nutrition intervention baseline survey and universal salt iodization monitoring at household level |  | a l
Facility Security |  | No. of CCTV | 150 | 30 |  | The 30 CCTV cameras were
|  | cameras installed |  |  |  | installed in the first phase.
| No. of facilities fenced |  | 70 | 4 | The four health facilities (Blue Valley, Kangaru and Embu Level 5) were fenced with perimeter wall and Gikiiro was fenced with barbed were. All these were fenced in the first phase.
| No. of security officers trained |  | 135 | 0 |  | The security officers were
[6 empty] | not trained because they | a l
[6 empty] | were contracted | a l