## Sheet1
Sub-Programme |  | Performance | Target | Achieved | Comments
Indicator
| No of Products developed |  | 25 | 0 | Target was not Achieved.
Business Service Centre |  | No. of local and | 1 | 0 | The project was not implemented
international
marketing
activities
conducted
Programme: Investment
Investment |  | No. of investors | 100 | 20 |  | The department did not manage
|  | attracted |  |  |  | to identify the investments well.
Juakali sheds and SME Parks | No. of Juakali sheds and SME parks constructed |  | 40 | 0 | There were no JuaKali Sheds or SMEs parks constructed.
OVOP – One Village One Product |  | No. of SMEs | 500 | 37 | The target was not achieved.
trained on
Business
Management
and Technical
Training on value
addition
Programme: Tourism
Tourism Infrastructure Development |  | No. of feasibility | 25 | 0 | The target was not Achieved
studies for
Tourist sites
Identified
| No. of tourist sites identified |  | 5 | 0 | The project was not implemented due to lack of funds
| No. of hostels constructed |  | 1 | 0 |  | The project was not
implemented due to lack of
funds
| No. of routes mapped and surveyed |  | 1 | 1 | This was achieved however clearing and murraming is required. Further KFS facilitation is also required to carry out an Audit on the work done.
|  | No. of tented | 5 | 0 |  | The project was not
|  | camps |  |  |  | implemented none creation of a
|  | constructed |  |  |  | management plan.