## Sheet1
Sub Programme |  |  | Key | Targets | Achievements | Remarks
performance
Indicators
Programme: General Administration, Planning and Support Services
Water Policy and regulatory framework |  | No. of regulations developed |  | 7 | 2 | Thia was not achieved fully due to inadequate technical capacity to undertake the project
Monitoring and Evaluation |  |  | No. of | 5 | 5 | The target was achieved
monitoring
reports
Public Participation |  | No. of Forums held |  | 100 | 70 | This was not fully achieved due to the COVID 19 Pandemic restrictions
| Human resource |  | No of staff | 248 | 248 | All Staff were remunerated
| development |  | remunerated
Office support services |  | No of staff supported |  | 248 | 248 | All Staff were supported
Design Review |  | No Of designs reviewed |  | 5 | 1 |  | The target was not
achieved.However,one design
was reviewed
Programme: Water Resource Management and Service delivery
Water storage and flood control |  |  | No. of | 55 | 18 | Eighteen earth dams were established and desilted
Sand-dams,
earth dams and
water pans
established and
desilted
|  | No. of tanks constructed and rehabilitated |  | 20 | 29 | Four tanks were constructed and 25 plastic tanks with a capacity of 10,000 liters were purchased and installed