## Sheet1
Sub-Programme |  |  | Key | Targets | Achievements | Comments
Performance
|  |  | Indicators |  |  |  |  | o t
This occasioned huge
[7 empty] | pending bills in the Plan | o t
[7 empty] | period. | o t
Programme: County Assembly Infrastructure Improvement
County Assembly Office Complex | County Assembly | Percentage Level of completion of the County Assembly Office block |  | 350,000,000 | 144,000,000 |  | This was not been fully | o t
| Office Complex | [5 empty] | achieved due to the delayed
exchequer releases for this
project in the Plan period.
The level of completion is
[7 empty] | at 52% | o t
County Assembly Speaker’s Residence |  | Percentage Level Of Completion |  | 60,000,000 | 0 |  | The target was not | o t
[7 empty] | achieved. This was not | o t
implemented despite the
[7 empty] | budgetary provision in the | o t
[7 empty] | Plan period due to the non- | o t
availability of the land.
| Acquisition Of | Percentage Level of Acquisition |  | 10,000,000 | 0 | The target was not achieved. This was due to the non-availability of land | The target was not | o t
| Land for The | [5 empty] | achieved. This was due to | o t
| Speaker’s | [5 empty] | the non-availability of land | o t
Residence
Renovation Of the County Assembly Chambers | Renovation Of the | Percentage Level of Renovation of The Chambers |  | 10,000,000 | 20,000,000 |  | The target was achieved at | o t
| County Assembly | [5 empty] | 100%. The Chambers were | o t
| Chambers | [5 empty] | fully renovated and
operationalized.